## Dashboard
MOSAIC-SoC — Project Dashboard
IEEE SSCS Chipathon 2026 · Track D · Team D15 JustVibeAndTapeout · github.com/MILOUDIAS/MOSAIC-SoC
OVERALL PROGRESS
Tasks Complete |  | % Complete | In Progress | Blocked
KEY MILESTONES
# | Milestone | Target Date | Week | Gate | Status
M0 | Proposal accepted, team locked | Jun 12 | W24 | Done | Done
M1 | Environment + schema + SCI wrappers pass formal | Jun 26 | W26 | Internal | Done (functional; riscv-formal deferred)
M2 | RTL elaboration review (config → RTL) | Jul 3 | W27 | Review | Done Jun 30 — full-SoC elaboration clean
M3 | Per-core verification clean | Jul 10 | W28 | Review | Done Jul 10 — all suites green
M4 | Full-SoC sim + scheduler demo → GO/NO-GO | Jul 17 | W29 | CRITICAL | Ready — sim + sched demo already green
M5 | First DRC-clean P&R (dry-run GDS) | Jul 31 | W31 | Dry-run | Done Aug 1 — Block A macro DRC/LVS clean (Magic 0, KLayout 0, Netgen "circuits match uniquely", XOR 0, antenna 0, IR 104 uV)
M6 | Top-level layout + LVS clean | Aug 21 | W34 | Review | In Progress - macro re-hardened 2026-08-02 with the bug-31 fix: DRC/LVS/XOR/antenna all 0, max-cap 0, max-fanout 1, max-slew 591 vs the library's 4.0 ns. Top-level layout is the MPW integrator's
M7 | FINAL DRC-clean GDSII submitted | Aug 28 | W35 | FINAL | Not Started — blocked on re-harden + slew/cap/fanout repair
Update task statuses in the Tasks sheet — the KPI cards above recalculate automatically.
Dates are subject to change (per organisers). Re-check the schedule repo & Discord each phase.
M: stands for Milestone

## Tasks
Task Tracker
Set Status to Done / In Progress / Blocked / Not Started — Dashboard rolls these up. Owner & dates editable.
Phase | Task | Owner | Week | Status | Start | Due | Notes / Deliverable
Phase 2 | Scaffold repo (rtl/ config/ flow/ verif/ agent/) | All | W24 | Done | Jun 12 | Jun 18 | Repo live: hw/ util/ tb/ sw/ flow/ harness/ configs/ refs/
Phase 2 | Pin IIC-OSIC-TOOLS container + commit hash | All | W24 | In Progress | Jun 12 | Jun 18 | Local toolchain in use; Verilator pinned to 5.050 (bug 21). Container pin + docs/ENV.md still open
Phase 2 | CI runs make lint on push | All | W24 | Not Started | Jun 14 | Jun 20 | GitHub Actions not set up yet
Phase 2 | mosaic.yaml schema v0 (JSON-Schema) | MILOUDIAS | W25 | Done | Jun 19 | Jun 25 | Python-validated schema (mosaic_config.py) + bus_opts validation; 15 pytests green
Phase 2 | SCI (OBI 1.3) wrapper spec | MILOUDIAS | W25 | Done | Jun 19 | Jun 25 | SCI spec realised in 3 wrappers (fazyrv/serv/ibex): OBI bridge, dormancy + sleep/wake handshake, core_sleep_o
Phase 2 | Wrap SERV in SCI; builds | MILOUDIAS | W25 | Done | Jun 22 | Jun 28 | serv_sci.sv verified: cocotb wake-loop + full-SoC firmware sim (QERV reuses it at W=4)
Phase 2 | SERV & FazyRV pass riscv-formal | yacine-hk | W26 | Not Started | Jun 26 | Jul 2 | Deprioritised: functional verification via cocotb + full-SoC sims instead (riscv-formal = stretch, N-09)
Phase 2 | config-author skill scaffold (NL→YAML) | trabdelbasset | W26 | Done | Jun 26 | Jul 2 | harness/skills/config_author.py: generate/validate, 3 presets, CLI
Phase 3 | Generator emits RTL + memory map from config | MILOUDIAS | W27 | Done | Jul 3 | Jul 9 | mcu_gen.py + 37 Mako templates; make mosaic-gen EXIT=0; memory map emitted (M2 passed Jun 30)
Phase 3 | Integrate OBI crossbar + Task Dispatch Unit | MILOUDIAS | W27 | Done | Jul 3 | Jul 9 | TDU 22/22 unit + SoC cocotb; THREE fabrics done: OBI xbar, log (LIC), FlooNoC. GE count pending synthesis
Phase 3 | Per-core RISC-V Arch Tests via cocotb | yacine-hk | W28 | In Progress | Jul 10 | Jul 16 | Functional per-core sims green for all 9 cores (SCI cocotb, all-TITAN SMP, picorv32/snitch/cva6 wake demos); official arch-test suite not run
Phase 3 | Peripheral tests (UART/GPIO/timer) | yacine-hk | W28 | Not Started | Jul 10 | Jul 16 | Peripherals only exercised implicitly (soc_ctrl, SPI boot path) — no dedicated UART/GPIO/timer TB yet
Phase 3 | Full-SoC Verilator sim (sensors+IIR+UART) | MILOUDIAS | W29 | Done | Jul 17 | Jul 17 | Early (Jul 9): run_fw.sh production C firmware on 7-hart PoC — EXIT SUCCESS (D-60); workloads via TDU tasks
Phase 3 | TDU scheduler demo (3 modes, migration ≤2 ticks) | MILOUDIAS | W29 | Done | Jul 17 | Jul 17 | titan_scheduling_demo.c: static / dynamic (CPI) / power-aware phases build & run (D-39)
Phase 3 | flow-runner drives first synthesis | trabdelbasset | W29 | In Progress | Jul 17 | Jul 17 | flow-runner skill done (11 flows, log parsing); first real synthesis run still pending PDK setup
Phase 4 | Full Librelane flow to GDSII | yacine-hk | W30 | In Progress | Jul 24 | Jul 30 | LibreLane flow wired (configs, PDN, SDC); blockers: mosaic_soc_core.sv pin-binding (P-01), SRAM macros (P-03)
Phase 4 | First DRC-clean GDSII + STA @ 50MHz | yacine-hk | W31 | Not Started | Jul 31 | Jul 31 | Needs P-01..P-03 + GF180 PDK first
Phase 4 | Padframe (22 pins, ¼ block) + ESD ring | yacine-hk | W32 | In Progress | Aug 7 | Aug 13 | GF180 pad frame chip_top.sv elaborates clean (D-31); pad map slot_mosaic.yaml completion open (P-02)
Phase 4 | drc-triage skill live + log metrics | trabdelbasset | W33 | In Progress | Aug 14 | Aug 20 | drc-triage skill implemented + tested (Magic/KLayout/Netgen parsers, D-43); awaiting real DRC runs for metrics
Phase 4 | Top-level DRC + LVS clean | yacine-hk | W34 | Not Started | Aug 21 | Aug 21 | Layout Review top (M6)
Phase 4 | doc-gen: memory-map + run report | yacine-hk | W34 | Done | Aug 21 | Aug 21 | doc-gen skill: config summary, memory map, run reports, dashboard parse (D-44)
Phase 4 | FINAL DRC-clean GDSII + metrics + repro pkg | All | W35 | Not Started | Aug 28 | Aug 28 | FINAL submission (M7)
Phase 5 | Write bring-up test plan | yacine-hk | W35 | Not Started | Aug 28 | Aug 31 | UART loopback, sensor smoke, sched toggle
Phase 5 | Archive reproducibility container | trabdelbasset | TBD | Not Started |  |  | Await organiser fab dates
Phase 3 | Multi-fabric system bus: bus: obi ¦ log (2-tier LIC) ¦ floonoc (AXI NoC + OBI bridges) | MILOUDIAS | W27 | Done | Jul 5 | Jul 9 | D-54..57: tb/log_xbar 5/5, bridge+NoC cocotb, wake demo EXIT SUCCESS ×3 fabrics
Phase 3 | iDMA integration (reg frontend + ND midend + OBI backend) | MILOUDIAS | W26 | Done | Jun 29 | Jun 30 | D-16: rewritten idma_xheep_wrapper; cocotb PASS at block + SoC level
Phase 3 | TDU wake→core loop + worker dormancy (per-hart fetch-enable gating) | MILOUDIAS | W26 | Done | Jun 29 | Jun 30 | D-17: cocotb end-to-end — no-wake parked / selective wake / all run
Phase 3 | Production C firmware (TDU driver + TITAN orchestrator + ASM workers) on 7-hart PoC | MILOUDIAS | W28 | Done | Jul 8 | Jul 9 | D-60: EXIT SUCCESS — 6 workers pop unique descriptors, per-slot sentinels + results verified
Phase 3 | cv32e40x integration + all-TITAN 4-core SMP demo (2×cv32e20 + 2×cv32e40x) | MILOUDIAS | W28 | Done | Jul 10 | Jul 10 | D-61/62: EXIT SUCCESS on obi/log/floonoc (17/8/58 µs); core bumped to post-0.10, XIF compat shim
Phase 3 | Debug: Verilator nightly DFG miscompile of cv32e40x hazard halt (bug 21) | MILOUDIAS | W28 | Done | Jul 10 | Jul 10 | RTL exonerated (-O0 + -fno-dfg discriminators); pinned Verilator 5.050 in all run scripts
Phase 2 | oh-my-soc harness: core + flow-runner/drc-triage/doc-gen/topo-viz skills + CLI | trabdelbasset | W26 | Done | Jun 30 | Jul 9 | D-40..45, D-58: 5 skills; python -m harness <skill> <cmd>; pytest green
Phase 3 | Full regression suite (18 steps: TDU unit/SoC, LIC, iDMA, NoC, SCI, wake ×3 fabrics, new-core demos ×4, all-TITAN ×3, prod fw, pytest) | MILOUDIAS | W28 | Done | Jul 10 | Jul 11 | Sweep 2026-07-11: ALL PASS (18/18) under pinned Verilator 5.050
Phase 3 | PicoRV32 integration (YosysHQ f00a88c vendor + picorv32_sci native-mem→OBI wrapper) | MILOUDIAS | W28 | Done | Jul 11 | Jul 11 | D-63: mosaic_picorv32.yaml wake demo EXIT SUCCESS (2 picorv32 workers); passed first run
Phase 3 | Snitch bare-core integration (mempool vendor + snitch_sci reqrsp→split-OBI wrapper) | MILOUDIAS | W28 | Done | Jul 11 | Jul 11 | D-64: mosaic_snitch.yaml wake demo EXIT SUCCESS; 3 documented vendored-file divergences (X-poison ifdefs, fork fpnew blobs)
Phase 3 | CVA6 32-bit SIM-ONLY integration (MOSAIC config pkg: uncached D-side/WT cache/CVXIF off + burst 64→32 AXI→OBI bridge + cva6_sci) | MILOUDIAS | W28 | Done | Jul 11 | Jul 11 | D-65: mosaic_cva6.yaml EXIT SUCCESS (cva6 TITAN orchestrates TDU); 1-patch bring-up; GF180 tapeout exclusion stands
Phase 3 | Combined new-cores demo: cva6 TITAN + snitch ATLAS + picorv32 NANO in one SoC | MILOUDIAS | W28 | Done | Jul 11 | Jul 11 | D-66: mosaic_new_cores.yaml EXIT SUCCESS — CVA6 wakes both workers via the TDU, per-slot sentinels verified
Phase 3 | test_new_cores.py pytest suite (registry/SCI/config parsing for the 3 new cores) | MILOUDIAS | W28 | Done | Jul 11 | Jul 11 | 11/11 pass; total generator pytests now 26
Phase 3 | Selectable platform blocks: soc.dma/debug/plic/spi_mode/multicore_timer/gpio_ao/ao_rv_timer/ao_fast_intr | MILOUDIAS | W31 | Done | Jul 29 | Jul 31 | 8 new schema knobs + template gates & tie-offs; 71 tests in test_dma_selection.py; suite 636 green
Phase 3 | GF180 area study: measured reduction 3.903 -> 1.249 mm2 (-68%) | MILOUDIAS | W31 | Done | Jul 29 | Jul 31 | docs/area_study_gf180_min_soc.md 8c-8g; every step measured (yosys 0.62+slang, tt/25C/5v00)
Phase 3 | Chipathon MPW Block A: 22-pin macro, routed GDS in 1117.5um slot | MILOUDIAS | W31 | Done | Jul 30 | Jul 31 | mosaic_block_a.sv; die 1117.5x1117.5um=1.2488mm2; 0 routing DRC, 0 antenna; setup +20.67ns hold +0.075ns
Phase 3 | GF180 library findings: no latch cell, unattributed SRAM blackboxes, unmapped tristates | MILOUDIAS | W31 | Done | Jul 30 | Jul 31 | hw/asic/gf180/{tc_clk,gf180_sram_blackbox,sram_wrapper}.sv - icgtp_1 ICG bind, (* blackbox *), bufz_4
Phase 3 | PDN core ring on Metal2/3 conflicts with router layer range | MILOUDIAS | W31 | Done | Jul 30 | Jul 30 | All detailed-routing violations were signal-to-VDD shorts on Metal3 along the ring; ring removed
Phase 3 | DRC + LVS signoff on Block A GDS | MILOUDIAS | W31 | Not Started | Aug 1 | Aug 21 | BLOCKER for submission. Magic/KLayout DRC + Netgen LVS never run on this GDS; status UNKNOWN not clean
Phase 3 | Block A power delivery (PSM-0069) unresolved | MILOUDIAS | W31 | Not Started | Aug 1 | Aug 21 | PDN_CORE_RING:false leaves PSM without a power source; IR drop unanalysed
Phase 3 | Confirm Block A pin contract with MPW integrator | MILOUDIAS | W31 | Not Started | Aug 1 | Aug 7 | 22 pins; bufz_4 QSPI drive is a placeholder; status_o[6:0] must be bonded (only observability, debug:false)

## Chipathon Schedule
Official Chipathon 2026 Schedule (with our Track D mapping)
Source: github.com/sscs-ose/sscs-chipathon-2026/schedule · all dates subject to change · weekly report due each Wednesday
Week | Date | Official Event | Phase | Our Track D Equivalent / Action | Our Milestone
W19 | May 8 | Kick-off Meeting | 1 Setup | (pre-team) intro to phases | —
W20 | May 15 | Tool Installation | 1 Setup | Librelane / DRC-LVS tutorials | —
W21 | May 22 | Tutorial Sessions | 1 Setup | MOSbius / gLayout | —
W22 | May 29 | Tutorial Sessions | 1 Setup | Charlib / ORFS / analog flows | —
W23 | Jun 5 | Team Formation Deadline | 2 Planning | Chip design with AI/LLM (Mehdi) | —
W24◄ | Jun 12 | Project Proposal Review | 2 Planning | Pitched proposal; begin build | M0 ✓
W25 | Jun 19 | Advanced Topics | 2 Planning | Schema v0 + SERV SCI wrapper | → M1
W26 | Jun 26 | Analog Design Ideas | 2 Planning | Formal verify wrappers; config-author scaffold | M1
W27 | Jul 3 | Schematic Review | 3 Design/Sim | RTL elaboration + config schema review | M2
W28 | Jul 10 | Simulation Review (blocks) | 3 Design/Sim | Per-core cocotb verification | M3
W29 | Jul 17 | Sim Review (top) + GO/NO-GO | 3 Design/Sim | Full-SoC sim + scheduler demo | M4 CRITICAL
W30 | Jul 24 | Layout Tutorial (DRC/LVS/PEX) | 4 Layout | Full Librelane flow to GDSII | —
W31 | Jul 31 | DRC Dry-run → GDS to partner | 4 Layout | First DRC-clean GDSII; STA @50MHz | M5
W32 | Aug 7 | Integration Tutorial | 4 Layout | Padframe + ESD + top integration | —
W33 | Aug 14 | Layout Review (blocks) | 4 Layout | drc-triage live; log metrics | —
W34 | Aug 21 | Layout Review (top) + DRC dry-run | 4 Layout | Top-level DRC + LVS clean; doc-gen | M6
W35 | Aug 28 | Verification + FINAL Submission | 4 Layout | Final DRC-clean GDSII + metrics | M7 FINAL
TBD | TBD | Chips available / test upload | 5 Mfg | Bring-up test plan ready | —

## Risks
Risk Register
Likelihood × calendar trigger × mitigation. Review at every weekly Zoom.
Risk | Likelihood | Decision Trigger | Mitigation | Status
On-chip SRAM too large for ¼ block | Low | Resolved Jul 31 | Measured: GF180 SRAM macros are area-NEGATIVE below ~512 B (4x sram64x8 = 0.402 mm2 vs ~0.252 mm2 of flip-flops). Frozen part uses a 128 B flip-flop scratchpad, sram_kb: 0 | Resolved
Agent produces invalid config / flow steps | Medium | Continuous | Every output gated by schema validation + log parsing; manual flow path always available | Mitigated
FazyRV not characterised on GF180MCU | Low | N/A for tapeout | FazyRV is not in the frozen Block A config (2x SERV). Remains sim-verified in the generator | Closed
Timing not closing @ 50 MHz | Low | Resolved Aug 1 | Frozen part runs at 10 MHz (CLOCK_PERIOD 100) with +20.72 ns setup / +0.055 ns hold worst-corner, TNS 0 at all 9 corners. 50 MHz was dropped deliberately per reviewer advice | Resolved
Team bandwidth (3 people, summer) | Medium | Weekly Zoom | Strict scope: PoC committed, all else stretch; cut stretch first | Watching
Simulator miscompile: oss-cad-suite Verilator nightly DFG bug (bug 21) | High (hit) | Hit Jul 10 (all-TITAN demo) | Pinned stable Verilator 5.050 in all sim scripts (VERILATOR_PIN override) | Mitigated
GF180 PDK + SRAM bitcell availability for signoff runs | Medium | Week 30 (layout phase start) | IIC-OSIC-TOOLS container or remote server; extract cell1rw from PDK or upstream OpenRAM | Watching
Signed-off GDS predates the bug-31 fix | Closed | Resolved Aug 2 | Re-hardened with the fix in place; all decks clean at lower utilization (84.4%) than before | Resolved
Electrical rule violations not covered by any deck | Medium | Before tapeout | max-cap 27->0, max-fanout 411->1, max-slew 2889->591 (measured against the library 4.0 ns rather than a tighter blanket default). Residual 591 needs per-net work: CTS_MAX_CAP and bufz_8 pad upsizing were both measured to make it worse | Open, reduced
Hand-modified vendored RTL untested | Medium (hit) | Continuous | UART FIFOs cut 32->4 entries for area with no test. Closed by tb/mosaic_soc/run_uart.sh, which measures the depth directly and checks TX against the UART DPI log | Mitigated
Timing-annotated GLS unavailable with open tools | Certain (hit) | Before tapeout | PDK cell models use ifnone on edge-sensitive specify paths (illegal per IEEE 1364-2005 14.2.6); iverilog and CVC both reject, CVC then segfaults on the full netlist. Functional GLS passes; timing coverage rests on STA at 9 corners | Open - needs commercial simulator

## Weekly Reports
Weekly Report Log
Organisers require a report every Wednesday. Log submission + 3-line summary here.
Week | Wed Date | Submitted? | Done this week | Blockers | Next week
W24 | Jun 17
W25 | Jun 24
W26 | Jul 1 |  | Config-driven multi-core generator sprint: YAML config system, SCI wrappers (serv/fazyrv/ibex), TDU 22/22, iDMA, multi-core sims 3/3 (Jun 27-30)
W27 | Jul 8 |  | Multi-fabric bus (obi/log/floonoc) + wake demo ×3; OpenRAM GF180 port + LibreLane SRAM wiring; oh-my-soc harness (5 skills)
W28 | Jul 15 |  | Production fw on 7-hart PoC EXIT SUCCESS; cv32e40x + all-TITAN 4-core SMP demo ×3 fabrics; bug 21 (Verilator DFG) root-caused, 5.050 pinned; NEW CORES: picorv32 + snitch + cva6(32-bit, sim-only) each sim-verified and running together (mosaic_new_cores.yaml); 18-step regression ALL PASS
W29 | Jul 22
W30 | Jul 29 |  | Area reduction 3.903 -> 1.249 mm2 by measurement; 8 selectable platform knobs; Block A 22-pin macro wrapper; first routed GDS in the Chipathon slot | DRC/LVS not yet run | Run the full signoff decks
W31 | Aug 5 |  | Block A re-hardened with the bug-31 fix: all decks clean, max-cap 27->0, max-fanout 411->1, max-slew 2889->591. RTL frozen + tagged rtl-freeze-blocka-v2. Gate-level simulation on the routed netlist passes (12 399 cycles vs RTL 12 400). UART bring-up test added | Timing-annotated GLS blocked: PDK models use illegal ifnone edge paths (IEEE 1364-2005 14.2.6) and CVC segfaults at this scale; 591 max-slew violations remain | Per-net slew work; consider a commercial simulator for SDF GLS
W32 | Aug 12
W33 | Aug 19
W34 | Aug 26
W35 | Sep 2